## Sheet1
Pre-Requsite Requirements | Responsible Party | Status | Notes | Category
SQL Server 2016 SP3 or later is installed |  | Not Started |  | Supported Upgrade Path
Processor: x64, minimum 1.4 GHz (2.0 GHz recommended) |  | Not Started |  | Hardware
Memory: Minimum 1 GB (4 GB or more recommended) |  | Not Started |  | Hardware
Disk Space: Minimum 6 GB on system drive |  | Not Started |  | Hardware
Display: Super VGA (800x600) or higher |  | Not Started |  | Hardware
Operating System: Windows Server 2016 or later |  | Not Started |  | Software
.NET Framework 4.7.2 is installed |  | Not Started |  | Software
Network Protocols: Shared Memory, Named Pipes, TCP/IP enabled |  | Not Started |  | Software
SQL Server Setup Components: ODBC Driver 17, OLE DB Driver |  | Not Started |  | Software
Upgrade account has local admin rights |  | Not Started |  | Security
Upgrade account has sysadmin privileges on SQL Server |  | Not Started |  | Security
All system and user databases are backed up |  | Not Started |  | Security
Antivirus/endpoint protection temporarily disabled |  | Not Started |  | Security
Run Data Migration Assistant (DMA) for deprecated features |  | Not Started |  | Compatibility
Check compatibility level and deprecated syntax |  | Not Started |  | Compatibility
Review SSIS/SSRS/SSAS package compatibility |  | Not Started |  | Compatibility
Review new features in SQL Server 2022 |  | Not Started |  | Compatibility
Open required ports: 443, 53, 9354, 445, 12000 |  | Not Started |  | Network
Firewall and NSG rules allow SQL traffic |  | Not Started |  | Network
DNS resolution and Azure endpoint connectivity validated |  | Not Started |  | Network
Perform test upgrade in non-production environment |  | Not Started |  | Testing
Validate application compatibility |  | Not Started |  | Testing
Compare performance against baseline |  | Not Started |  | Testing
Validate security configurations |  | Not Started |  | Testing
Enable Query Store for performance monitoring |  | Not Started |  | Testing
Upgarde Task Description | Responsible Party | Status | Notes
Inventory and Compatibility Check |  | Not Started
Decide on Migration Type (In-place or Side-by-Side) |  | Not Started
Evaluate Application Dependencies |  | Not Started
Take Full Backups of All Databases |  | Not Started
Capture Performance Baseline |  | Not Started
Audit Security (Logins, Roles, Permissions) |  | Not Started
Clean Up Unused Features |  | Not Started
Install SQL Server 2022 |  | Not Started
Migrate Databases (Backup/Restore, Detach/Attach, etc.) |  | Not Started
Migrate Logins, Jobs, Linked Servers |  | Not Started
Validate Application Connectivity |  | Not Started
Compare Performance with Baseline |  | Not Started
Verify Security Configuration |  | Not Started
Remove Deprecated Components |  | Not Started
Enable Query Store |  | Not Started
Monitor with Extended Events/Azure Monitor |  | Not Started
Enable New Features (e.g., IQP, ADR) |  | Not Started